## Laytime
Saltmarsh Shipping Ltd – laytime calculation, MV Northern Star
Voyage charterparty dated 12 March 2026 – 5,200 tonnes of packaged sawn timber discharged at Hartmouth – laytime and demurrage under clauses 9 and 10. Prepared by Priya Nair, Ashcombe Reeve LLP, 22 September 2026 (our ref TR/1001.1/PN). All times are in 2026, local time at Hartmouth; times in blue are taken from the master’s log and the harbour notices, and everything else is calculated.
From the charterparty and the master’s log
Laytime allowed (clause 9) | 6 | weather working days
Demurrage rate (clause 10) | 18000 | a day, pro rata
Notice of readiness given | 2026-08-03 10:24
Discharge completed | 2026-08-19 16:24
Owners’ calculation (Dunmere Pryce LLP, 15 September 2026) |  |  |  | Charterers’ calculation (clause 9)
Period | From | To | Days | Period | From | To | Counts? | Days
Laytime from notice | 2026-08-03 10:24 | 2026-08-09 10:24 | 6 | Laytime starts (clause 9.2) | 2026-08-04 08:00 | 2026-08-07 | Yes | 2.6667
Demurrage to completion | 2026-08-09 10:24 | 2026-08-19 16:24 | 10.25 | Weather stoppage (41/26, 42/26) | 2026-08-07 | 2026-08-09 | No | 0
|  |  |  | Sunday 9 August, also weather | 2026-08-09 | 2026-08-10 | No | 0
|  |  |  | Weather stoppage continues | 2026-08-10 | 2026-08-11 | No | 0
|  |  |  | Discharge resumes; laytime runs out | 2026-08-11 | 2026-08-14 08:00 | Yes | 3.3333
|  |  |  | Laytime used |  |  |  | 6
|  |  |  | On demurrage: every hour counts | 2026-08-14 08:00 | 2026-08-19 16:24 | Yes | 5.35
Days on demurrage |  |  | 10.25 | Days on demurrage |  |  |  | 5.35
Demurrage at the daily rate |  |  | 184500 | Demurrage at the daily rate |  |  |  | 96300
Difference between the two calculations (owners’ figure less charterers’ figure) | [7 empty] | 88200
Notes
1. Clause 9.2 starts laytime at 08:00 on the working day after notice of readiness, so the charterers’ calculation starts at 08:00 on Tuesday 4 August; the owners count from the notice itself.
2. Clause 9.4: no time counts while weather stops discharge. Harbour notices 41/26 and 42/26 and the master’s log put the stoppage at 00:00 on Friday 7 August to 24:00 on Monday 10 August; 9 August was also a Sunday, not used.
3. Sunday 16 August counts in full because the vessel was already on demurrage (clause 10.2): once on demurrage, every hour counts, including Sundays, holidays and weather.
Formulas:
From = [To, row above]
To = [From]+B5
To = ROUND(([From]+(B5-SUM(J12:[Days, row above])))*1440,0)/1440