## Due diligence
Kestrel Software Ltd – Series A due diligence tracker
Updated 28 September 2026
Prepared by Priya Nair for Helen Ashcombe (matter 1003.1). The requests are those of Brindley Moss LLP’s list of 21 September 2026. With is who provides the item. Status is Done, With client (the company has the next step) or Open (not yet started or not yet found).
Ref | Area | Request | With | Status | Date provided | Notes
DD01 | Corporate | Certificate of incorporation and current articles of association | Ines Kowalczyk | Done | 2026-09-22 | In the data room.
DD02 | Corporate | Registers of members, directors and people with significant control; share certificates | Ines Kowalczyk | Done | 2026-09-24 | Agree with the cap table: 9,000,000 ordinary shares.
DD03 | Corporate | Share option plan rules and register of options granted | Tobias Wren | Done | 2026-09-24 | 640,000 granted; 360,000 not yet allocated.
DD04 | Corporate | Board minutes and shareholder resolutions for the last three years | Ines Kowalczyk | With client |  | Minutes for 2024 still being found.
DD05 | Corporate | Waivers of pre-emption rights from Ruth Calloway and Dev Mistry | Ines Kowalczyk | With client |  | Helen has advised; Ines to ask both angels to sign.
DD06 | Intellectual property | IP assignment from Owain Rhys for the 2021 reporting module | Tobias Wren | Open |  | None signed. Tobias to contact Owain Rhys.
DD07 | Intellectual property | IP clauses in the contracts of staff and contractors who have written code | Tobias Wren | Done | 2026-09-25 | Staff contracts assign IP to the company. Contractors: see the row above.
DD08 | Intellectual property | Open-source components in Kestrel Rota and the desktop app, with their licences | Tobias Wren | With client |  | Tobias is running a scan of both.
DD09 | Customers | Top ten customer contracts | Ines Kowalczyk | Done | 2026-09-25 | Brackenmoor Care Homes contract has a change-of-control clause.
DD10 | Customers | Revenue by customer for the last two years | Ines Kowalczyk | Done | 2026-09-23 | Brackenmoor Care Homes Ltd is 22% of revenue.
DD11 | Customers | Standard customer licence terms | Ines Kowalczyk | With client |  | Review under way (matter 1003.2).
DD12 | Employment | List of staff with job titles, salaries and notice periods | Ines Kowalczyk | Done | 2026-09-24
DD13 | Employment | Employment contracts for all staff and the founders’ service agreements | Ines Kowalczyk | With client |  | Founders’ agreements received; staff contracts to follow.
DD14 | Data protection | Privacy policy, records of processing and registration with the data protection regulator | Tobias Wren | Done | 2026-09-25
DD15 | Data protection | Record of data incidents in the last three years | Tobias Wren | Open |  | One customer incident, May 2026. Tobias to send the file.
DD16 | Data protection | Customer data-processing terms and list of sub-processors | Tobias Wren | With client |  | Sub-processor list being checked.
DD17 | Property | Lease of the office at Kingfisher Yard | Ines Kowalczyk | Done | 2026-09-23 | Lease ends March 2027.
DD18 | Disputes | Any claims, disputes or grievances in the last three years | Ines Kowalczyk | Done | 2026-09-24 | None.
DD19 | Finance | Statutory accounts for the last two years | Ines Kowalczyk | Done | 2026-09-22
DD20 | Finance | Management accounts to 31 August 2026 | Ines Kowalczyk | With client |  | Due from Ines this week.
DD21 | Finance | Confirmation that VAT and payroll taxes are up to date | Ines Kowalczyk | Open
DD22 | Finance | Loans, overdrafts and any charges over the company’s assets | Ines Kowalczyk | Done | 2026-09-23 | None.
Where things stand
Done |  |  | 12
With client |  |  | 7
Open |  |  | 3
All requests |  |  | 22
Done, as a share of all requests |  |  | 54.55%
Check: the counts above less all requests (nil) |  |  | 0